## Cover Page
Increasing Educator Diversity Plan
District:
Union School District
Team Lead:
Steve Jackopsic, Superintendent/Principal
Team Members:
BOE: Jim Kavanagh, Ed Fournier
Teachers/Staff: Patricia Zulick-Bessette, Michele Powers
Vision:
To create a diverse, talented, learning-centered, collaborative and passioniate staff
Theory of Action:
If Union School District implements policies, structures and practices in equitable hiring practices
Then the district staff will represent a diverse, collaborative group that will enable students to achieve to their full potential.
And, Union School District students will benefit from cultural connection and awareness.
Note-BOE Subcommittee reviewed on 10/31/24. BOE will review/approve at November meeting.

## Recruitment
Recruitment
Goal | Who Manages the Goal? | Strategies/Key Activities | Strategies/Key Activities | Strategies/Key Activities | Indicators of Progress | Resources Required | Risks and Mitigation | Communication & Engagement Efforts
|  | What? | Who? | When?
Recruit passionate and diverse qualified educatorswho apply for open positions within Union School District | Superintendent/Principal | Develop contacts with institutions (including job fairs, as needed) and other community organizations to publicize job openings and solicit referrals of qualified diverse candidates | Superintendent/Principal and Staff: Design leadership training focused on promoting diversity, cultural competence and awareness, sensitivity, and recognizing bias within the application process | By December 2025 | Increased number of diverse applicants, as assessed after the hiring and selection process has been finalized | Time to train leaders | Town demographics could hinder the district’s appeal to diverse candidates | Utilize local universities and colleges
|  | Include on the district website and in position postings a diversity statement along with a non-discrimination statement to inform applicants that the district values diversity | Provide training to school leaders/educators |  | Increased number of diverse student teachers (dependent on interest) in the district as assessed after the hiring and selection process has been finalized | Time to build and improve content | Discuss, as appropriate, w/ town leadership, BOE | Gain buy-in from district and town leaders
Methods to make job applications and descriptions more reflective of a community that values diversity

## Hiring and Selection
Goal | Who Manages | Strategies/ | Strategies/ | Strategies/ | Indicators of Progress | Resources Required | Risks and Mitigation | Communication & Engagement Efforts
| the Goal? | Key Activities | Key Activities | Key Activities
|  | What? | Who? | When?
Establish equitable hiring practices that reduce or eliminate the effects of unconscious and implicit bias | Driven by District Leaders | Select diverse interview committees (parents/staff) that include individuals with a wide range of experiences and perspectives | Ensure hiring staff has tools needed to track applicant flow, consistent with legal requirements, after the hiring and selection process concludes | Train between June 2025 to December 2025 | Increased number of diverse candidates selected to interview, as assessed after the hiring and selection process concludes | Interview checklist, notes | Volunteer- based committees limit willing participants | Identify the many staff members who may publicize job openings to potential candidates
| Monitored by Office Staff | Provide implicit bias and anti-bias training to all members of the hiring committee | Offer more than one round of interviews | Revisit changes and review data before the 2026 hiring season | Increased number of diverse candidates offered positions as assessed after the hiring and selection process concludes | Standard interview questions on cultural awareness | Conduct as few July and August interviews as possible | Ensure that these staff members understand the increased staff diversity plan, its goals, and its strategies
|  | Ask interview questions that reveal commitment to Board goals regarding cultural competency and creating a welcoming, safe, and inclusive school environment |  |  |  |  | Budget reductions may decrease future hiring and chances to diversify staff
|  | Post openings on various search engines |  |  |  |  | Offer pay or incentives to serve on committees

## Retention
Retention
Goal |  | Strategies/Key Activities | Strategies/Key Activities | Strategies/Key Activities | Indicators of Progress | Resources Required | Risks and Mitigation | Communication & Engagement Efforts
Who Manages the Goal?
|  | What? | Who? | When?
Maintain an environment where everyone, including diverse employees, feels safe, welcome, and valued | Superintendent/Principal and Staff | Prioritize cultural awareness, competence, and responsiveness throughout the district | Superintendent/Principal, teachers | On-going | Climate data reflects that stakeholders (including staff, students, and families) feel connected to the school community | Maintain staff funding levels | Budget cuts could prevent retention of diverse staff (most recent hires can be the first to be cut) | Discuss goals with Board of Education
| Board of Education | Provide opportunities for staff to interact with all members of our educational community and discuss areas of interest or concern | TEAM District Facilitator | Annual data analysis | Curriculum writing and revisions include a more in-depth lens with input from a diverse pool of staff with varied perspectives, expertise, and interests | Provide time for leaders to train employees and committees | Garner diversity plan buy-in from both town and district decision- makers | Collaboration with TEAM district facilitator and building leaders to recruit mentors from the entire school community
|  | Provide TEAM mentors with resources to provide adequate support and encouragement to mentees | Building Leaders |  | Climate data that shows job satisfaction of all staff, including diverse staff | Compensate mentors